## Performance Metrics
|  | Western Area Power Administration | Effective: | 2016-12-31
|  | Rocky Mountain Region (LAPT & CRCM) | Posted: | 2017-01-11
Performance Metrics
Transmission Service Requests and Studies
|  |  | 1st Qtr 2016 |  | 2nd Qtr 2016 |  | 3rd Qtr 2016 |  | 4th Qtr 2016
• Process time from initial service request to offer of SIS agreement |  |  | Non-Affiliate | Affiliate | Non-Affiliate | Affiliate | Non-Affiliate | Affiliate | Non-Affiliate | Affiliate
| • Number of new SIS agreements delivered |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| • Number of new SIS agreements delivered more than 30 days after request submittal |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| • Average time (days) from request submittal to change in request status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| • Average time (days) from request submittal to delivery of SIS agreement |  | 24 | 0 | 0 | 0 | 0 | 0 | 92 | 0
| • Number of new SIS agreements executed |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
• SIS processing time
| • Number of SIS completed |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| • Number of SIS completed more than 60 days after executed SIS agreement |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| • Average time (days) from receipt of executed SIS agreement to completed SIS available to transmission customer |  | 0 | 0 | 149 | 0 | 0 | 0 | 0 | 0
| • Average cost of SIS completed during the period |  | 0 | 0 | 16607.09 | 0 | 0 | 0 | 0 | 0
• For all SIS completed more than 60 days after receipt of executed SIS agreement, average number of days study was delayed due to transmission customer's actions |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
• Service requests withdrawn from SIS queue
| • Number of requests withdrawn from the SIS queue |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| • Number of SIS withdrawn more than 60 days after receipt of executed SIS agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| • Average time (days) from receipt of executed SIS agreement to date when request was withdrawn from SIS queue |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
• Process time from completed SIS to offer of FS
| • Number of new FS agreements delivered to transmission customers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| • Number of new FS agreements delivered to transmission customers more than 30 days after completion of SIS |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| • Average time (days) from completion of SIS to delivery of FS agreement |  | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0
| • Number of new FS agreements executed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
• FS processing time
| • Number of FS completed |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| • Number of FS completed more than 60 days after receipt of executed FS agreement |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| • Average time (days) from receipt of executed FS agreement to date when completed FS made available to transmission customer |  | 0 | 0 | 172 | 0 | 0 | 0 | 0 | 0
| • Average cost of FS completed during the period |  | 0 | 0 | 9510.46 | 0 | 0 | 0 | 0 | 0
| • Average cost of recommended upgrades for FS completed during the period |  | 0 | 0 | 905000 | 0 | 0 | 0 | 0 | 0
• For all FS completed more than 60 days after receipt of executed FS agreement, average number of days study was delayed due to transmission customer's actions |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
• Service requests withdrawn from FS queue
| • **Number of requests withdrawn from the FS queue |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| • Number of FS withdrawn more than 60 days after receipt of executed FS agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| • Average time (days) from receipt of executed FS agreement to date when request was withdrawn from the FS queue |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
** Requests were withdrawn after the completion of the SIS , prior to the execution of FS Agreement

## SIS Agreement
Process time from initial service request to offer of SIS agreement
[8 empty] | 1st Qtr 2016 |  | 2nd Qtr 2016 |  | 3rd Qtr 2016 |  | 4th Qtr 2016
[8 empty] | 2016-01-01 | 2016-03-31 | 2016-04-01 | 2016-06-30 | 2016-07-01 | 2016-09-30 | 2016-10-01 | 2016-12-31
| • Number of new SIS agreements delivered | [6 empty] | 2016-01-01: 1; 2016-04-01: 0; 2016-07-01: 0; 2016-10-01: 2
| • Number of new SIS agreements delivered more than 30 days after request submittal | [6 empty] | 2016-01-01: 1; 2016-04-01: 0; 2016-07-01: 0; 2016-10-01: 2
| • Average time (days) from request submittal to change in request status | [6 empty] | 2016-01-01: 0; 2016-04-01: 0; 2016-07-01: 0; 2016-10-01: 0
| • Average time (days) from request submittal to delivery of SIS agreement | [6 empty] | 2016-01-01: 24; 2016-04-01: 0; 2016-07-01: 0; 2016-10-01: 92
| • Number of new SIS agreements executed | [6 empty] | 2016-01-01: 1; 2016-04-01: 0; 2016-07-01: 0; 2016-10-01: 2
| Queue Number | Request Received | Offer SIS Agreement | Change Date | # Days | # Days before change | # Delivered | 2016-01-01: # Executed; 2016-03-31: > 30 Days
1st Qtr 2016 | 2016-T2 | 2015-12-11 | 2016-01-04 |  | 24 |  | 1 | bar: 2016-01-01 to 2016-03-31
2nd Qtr 2016
3rd Qtr 2016
4th Qtr 2016 | 2016-T10 | 2016-08-24 | 2016-12-01 |  | 99 |  | 1 | bar: 2016-01-01 to 2016-03-31
| 2017-T1 | 2016-10-03 | 2016-12-27 |  | 85 |  | 1 | bar: 2016-01-01 to 2016-03-31

## SIS
SIS processing time
[7 empty] | 1st Qtr 2016 |  | 2nd Qtr 2016 |  | 3rd Qtr 2016 |  | 4th Qtr 2016
[7 empty] | 2016-01-01 | 2016-03-31 | 2016-04-01 | 2016-06-30 | 2016-07-01 | 2016-09-30 | 2016-10-01 | 2016-12-31
| • Number of SIS completed | [5 empty] | 2016-01-01: 0; 2016-04-01: 1; 2016-07-01: 0; 2016-10-01: 0
| • Number of SIS completed more than 60 days after executed SIS agreement | [5 empty] | 2016-01-01: 0; 2016-04-01: 1; 2016-07-01: 0; 2016-10-01: 0
| • Average time (days) from receipt of executed SIS agreement to completed SIS available to transmission customer | [5 empty] | 2016-01-01: 0; 2016-04-01: 149; 2016-07-01: 0; 2016-10-01: 0
| • Average cost of SIS completed during the period | [5 empty] | 2016-01-01: 0; 2016-04-01: 16607.09; 2016-07-01: 0; 2016-10-01: 0
| Queue Number | Executed SIS Agreement | SIS Complete | # Days | Deposit ($) | Available ($) | 2016-01-01: Used ($); 2016-03-31: SIS Completed; 2016-04-01: > 60 Days
1st Qtr 2016
2nd Qtr 2016 | 2016-T2 | 2016-01-05 | 2016-06-02 | 149 | 50000 | 33392.91 | 2016-01-01: 16607.09; 2016-03-31: 2016-06-02; 2016-04-01: 1
3rd Qtr 2016
4th Qtr 2016

## FS Agreement
Process time from completed SIS to offer of FS
[7 empty] | 1st Qtr 2016 |  | 2nd Qtr 2016 |  | 3rd Qtr 2016 |  | 4th Qtr 2016
[7 empty] | 2016-01-01 | 2016-03-31 | 2016-04-01 | 2016-06-30 | 2016-07-01 | 2016-09-30 | 2016-10-01 | 2016-12-31
| • Number of new FS agreements delivered to transmission customers | [5 empty] | 2016-01-01: 0; 2016-04-01: 0; 2016-07-01: 0; 2016-10-01: 0
| • Number of new FS agreements delivered to transmission customers more than 30 days after completion of SIS | [5 empty] | 2016-01-01: 0; 2016-04-01: 1; 2016-07-01: 0; 2016-10-01: 0
| • Average time (days) from completion of SIS to delivery of FS agreement | [5 empty] | 2016-01-01: 0; 2016-04-01: 35; 2016-07-01: 0; 2016-10-01: 0
| • Number of new FS agreements executed | [5 empty] | 2016-01-01: 0; 2016-04-01: 0; 2016-07-01: 0; 2016-10-01: 0
| Queue Number | Completion of SIS | Offer Facility Study Agreement | # Days | # Delivered | # Executed | 2016-01-01: > 30 Days
1st Qtr 2016
2nd Qtr 2016 | 2015-T9 | 2015-11-16 | 2015-12-21 | 35 | bar: 2016-01-01
3rd Qtr 2016
4th Qtr 2016

## FS
FS processing time
[7 empty] | 1st Qtr 2016 |  | 2nd Qtr 2016 |  | 3rd Qtr 2016 |  | 4th Qtr 2016
[7 empty] | 2016-01-01 | 2016-03-31 | 2016-04-01 | 2016-06-30 | 2016-07-01 | 2016-09-30 | 2016-10-01 | 2016-12-31
| • Number of FS completed | [5 empty] | 2016-01-01: 0; 2016-04-01: 1; 2016-07-01: 0; 2016-10-01: 0
| • Number of FS completed more than 60 days after receipt of executed FS agreement | [5 empty] | 2016-01-01: 0; 2016-04-01: 1; 2016-07-01: 0; 2016-10-01: 0
| • Average time (days) from receipt of executed FS agreement to date when completed FS made available to transmission customer | [5 empty] | 2016-01-01: 0; 2016-04-01: 172; 2016-07-01: 0; 2016-10-01: 0
| • Average cost of FS completed during the period | [5 empty] | 2016-01-01: 0; 2016-04-01: 9510.46; 2016-07-01: 0; 2016-10-01: 0
| • Average cost of recommended upgrades for FS completed during the period | [5 empty] | 2016-01-01: 0; 2016-04-01: 905000; 2016-07-01: 0; 2016-10-01: 0
| Queue Number | FS Agreement Executed | FS Complete | # Days | Deposit ($) | Available ($) | 2016-01-01: Upgrades ($); 2016-03-31: Used ($); 2016-04-01: FS Completed; 2016-06-30: > 60 Days
1st Qtr 2016 |  |  |  | 0 |  |  | 2016-03-31: 0
2nd Qtr 2016 | 2015-T9 | 2015-12-21 | 2016-06-10 | 172 | 100000 | 90489.54 | 2016-01-01: 905000; 2016-03-31: 9510.46; 2016-04-01: 1; 2016-06-30: 1
3rd Qtr 2016
4th Qtr 2016
Note on K11: DFarm: Why is FERC tracking 60 days, when the tariff identifies 90 or 180?

## SIS Withdrawn
|  |  | 1st Qtr 2016 |  | 2nd Qtr 2016 |  | 3rd Qtr 2016 |  | 4th Qtr 2016
• Service requests withdrawn from SIS queue |  |  | 2016-01-01 | 2016-03-31 | 2016-04-01 | 2016-06-30 | 2016-07-01 | 2016-09-30 | 2016-10-01 | 2016-12-31
| • Number of requests withdrawn from the SIS queue |  | 2016-01-01: 0; 2016-04-01: 0; 2016-07-01: 0; 2016-10-01: 0
| • Number of SIS withdrawn more than 60 days after receipt of executed SIS agreement |  | 2016-01-01: 0; 2016-04-01: 0; 2016-07-01: 0; 2016-10-01: 0
| • Average time (days) from receipt of executed SIS agreement to date when request was withdrawn from SIS queue |  | 2016-01-01: 0; 2016-04-01: 0; 2016-07-01: 0
| Queue Number | Executed SIS | 2016-01-01: Date of Withdrawal; 2016-03-31: # Days; 2016-04-01: > 60 Days
1st Qtr 2016 | bar: 2016-03-31
2nd Qtr 2016
3rd Qtr 2016
4th Qtr 2016

## FS Withdrawn
|  |  | 1st Qtr 2016 |  | 2nd Qtr 2016 |  | 3rd Qtr 2016 |  | 4th Qtr 2016
• Service requests withdrawn from FS queue |  |  | 2016-01-01 | 2016-03-31 | 2016-04-01 | 2016-06-30 | 2016-07-01 | 2016-09-30 | 2016-10-01 | 2016-12-31
| • **Number of requests withdrawn from the FS queue |  | 2016-01-01: 0; 2016-04-01: 0; 2016-07-01: 0; 2016-10-01: 0
| • Number of FS withdrawn more than 60 days after receipt of executed FS agreement |  | 2016-01-01: 0; 2016-04-01: 0; 2016-07-01: 0; 2016-10-01: 0
| • Average time (days) from receipt of executed FS agreement to date when request was withdrawn from the FS queue |  | 2016-01-01: 0; 2016-04-01: 0; 2016-07-01: 0; 2016-10-01: 0
| Queue Number | Executed FS Agreement | 2016-01-01: Date of Withdrawal; 2016-03-31: # Days; 2016-04-01: > 60 Days
1st Qtr 2016 | bar: 2016-03-31
2nd Qtr 2016
3rd Qtr 2016
4th Qtr 2016