## Introduction
Entergy 2013-2017 Draft Construction Plan Update 2
Project Driver | Project Description | Cost Allocation Guideline | Project Category
Block load addition | Projects needed to accommodate the addition of block loads beyond expected normal load growth | Attachment T | CP (load related)
Load growth | Projects needed to reliably serve expected normal load growth | Attachment T | CP (load related)
Transmission Reliability - Maintaining Infrastructure | Projects needed to maintain existing infrastructure or existing levels of reliability | Attachment T | CP (AM related)
Transmission Reliability - Meeting Planning Criteria | Projects needed to meet NERC Reliability Standards, SERC Supplements, and Entergy Transmission Local Planning Criteria | ICT to determine | CP (others)
Transmission Reliability - Regulatory | Projects to satisfy regulatory requirements | ICT to determine | CP (others)
Transmission Service | Projects needed to accommodate new transmission service requests | ICT to determine | CP (others)
Economic | Projects anticipated to yield production cost savings | ICT to determine | CP (others)
Enhanced Transmission Reliability | Projects yielding transmission reliability levels above those specified in local planning criteria | ICT to determine | CP (others)
Customer Driven | Customer driven (other than reliability) | ICT to determine | CP (others)
Generation Interconnection | Projects to interconnect new generation | ICT to determine | CP (others)
Terminology (Funding Comments)
Approved | Project construction is funded and Entergy is committed to completing it by the projected in service date
Proposed & In Target | Project is currently funded for scoping and preliminary engineering and the expected construction commencement date is within the 5-year Construction Plan horizon
Not Funded | Project is currently outside the 5-year Construction Plan horizon. Project is not officially included in the budget forecast.
Caveats!
This list of approved and proposed projects is fluid.
Budget adjustments throughout the year could alter this list.
"Out-of-cycle" projects, such as customer-driven projects, could be appended to the list as needed.
Addendum: Horizon Projects
Horizon Projects are projects that have been identified in the annual 10 year reliability assesment but are not included in the current five year construction plan window. Final project scopes and timing may vary in future assessments.
Addendum: Identified Target Areas
Identified Target areas are areas of interest that may require reliability improvements beyond the 10 year planning horizon. Future changes in modeling assumptions may require the project or an equivalent type project to be included in the annual 10 year assessment.

## Others Header
Construction Plan Projects Relating To:
• Transmission Reliability - Meeting Planning Criteria • Transmission Reliability - Regulatory • Transmission Service • Economic • Enhanced Transmission Reliability • Customer Driven • Generation Interconnection

## CP (Others)
Entergy Draft 2013 - 2017 Construction Plan Update 2 Projects
2013 - 2017 Draft Construction Plan Update 1
New Project
Modified
Removed
Construction Plan ID | Project Driver | Project Name | LE | Proposed ISD (Planning) | 2012 Funding Comments | Project Status | Actual ISD | Other Comments
10-EAI-015-2-CP | Transmission Reliability - Meeting Planning Criteria | Holland Bottoms (Cabot EHV): Construct new 500/161/115 kV substation Phase 2 Projects(2012) Install 161 kV Bus and a 600 MVA 500 kV / 161 kV Autotransformer | EAI | 2012 Summer | Approved | Complete | 2012-05-23
10-EAI-017-CP | Transmission Reliability - Meeting Planning Criteria | Holland Bottoms - Hamlet 161 kV Line: Construct new 161 kV Line Convert Hamlet SS to a breaker station (Single Bus Single Breaker Scheme) Move the Quitman line from Gold Creek to Hamlet SS Move the Gravel Ridge line from Gold Creek to Hamlet SS Construct a line rated at least 1200 A from Hamlet SS to Holland Bottoms | EAI | 2012 Summer | Approved | Complete | 2012-05-23
10-EAI-018-CP | Transmission Reliability - Meeting Planning Criteria | Ebony 161 kV Switching Station: Install 5 Breaker Ring Bus Lines Terminating Into New Ebony Substation (ratings unchanged): Ebony - Kuhn Road 161 kV Line Ebony - WM Lehi - WM Polk - WM EHV 161 kV Line Ebony - WM Dover - WM Gateway 161 kV Line Ebony - Marked Tree 161 kV Line Ebony - WM Lehi - WM EHV 161 kV Line | EAI | 2012 Summer | Approved | Construction |  | May be delayed to the fall due to construction feasibility
10-EAI-019-CP | Transmission Reliability - Meeting Planning Criteria | Jonesboro to Hergett 161 kV Line: Upgrade 161 kV Line to at least 240 MVA | EAI | 2012 Summer | Approved | Complete | 2012-05-03
10-EAI-022-1-CP | Transmission Service | Westar Transmission Service Monette - Paragould 161kV Line: Upgrade to at least 246 MVA | EAI | 2012 Summer | Approved | Complete | 2012-01-10
10-EAI-022-2-CP | Transmission Service | Westar Transmission Service Paragould Substation: Upgrade the switch B6673 from 600A to 2000A | EAI | 2012 Summer | Approved | Complete | 2011-09-29
10-EAI-022-3-CP | Transmission Service | Westar Transmission Service Russellville South - Dardanelle Dam (SPA) 161kV Line: Upgrade to 416 MVA | EAI | 2012 Summer | Approved | Complete | 2011-10-31
11-EAI-001-CP | Transmission Reliability - Meeting Planning Criteria | Pine Bluff Voltage Support Project - Phase 1 Poyen 115 kV Substation: Add 21.6 MVAR Capacitor Bank | EAI | 2012 Summer | Approved | Complete | 2012-05-31
11-EAI-006-CP | Transmission Reliability - Meeting Planning Criteria | Ebony 161 kV Switching Station: Add 36 MVAR Capacitor Bank | EAI | 2012 Summer | Approved | Construction |  | May be delayed to the fall due to construction feasibility
11-EAI-010-CP | Transmission Reliability - Meeting Planning Criteria | Wilmar Substation: Add 21.6 MVAR Capacitor Bank (Formerly Hilo Substation) | EAI | 2012 Summer | Approved | Design/Scoping |  | May be delayed to the fall due to construction feasibility
13-EAI-007-CP | Transmission Reliability - Meeting Planning Criteria | Jim Hill to St. Francis 161 kV line: Upgrade terminal equiment at Jim Hill | EAI | 2012 Fall | Approved | Design/Scoping |  | New Project
10-EAI-020-CP | Transmission Reliability - Meeting Planning Criteria | Benton North to Benton South: Construct New 115 kV Line Rated at least 170 MVA Install Switching Stations at Benton North and Benton South | EAI | 2012 Winter | Approved | Design/Construction
12-EAI-028-CP | Transmission Reliability - Meeting Planning Criteria | Quitman to Bee Branch: Replace 600A switch | EAI | 2012 Winter | Proposed & In Target | Design/Scoping |  | Scope of project changed to equipment upgrade
11-EAI-009-CP | Generation Interconnection | Basin Springs Substation - Construct new substation | EAI | 2013 Summer | Approved | Design/Scoping |  | IA executed but currently on suspension per customer
11-EAI-012-CP | Transmission Reliability - Meeting Planning Criteria | Stuttgart Ricuskey 115 kV Substation: Expand Capacitor Bank to 39 MVAR | EAI | 2013 Summer | Proposed & In Target | Design/Scoping
11-EAI-026-CP | Transmission Reliability - Meeting Planning Criteria | NLR Westgate - NLR Levy: Reconductor 115 kV Line | EAI | 2013 Summer | Proposed & In Target | Design/Scoping
13-EAI-004-CP | Transmission Reliability - Meeting Planning Criteria | Monticello East - Add 21.6 MVAR capacitor bank | EAI | 2013 Summer | Proposed & In Target | Design/Scoping |  | Replaces Monticello East SVC project 12-EAI-007-CP
12-EAI-020-CP | Transmission Reliability - Meeting Planning Criteria | Mabelvale: Change 500-115 NLTC from 487.5kV tap to 512.5kV tap | EAI | 2013 Summer | Approved | Complete | 2012-05-10
11-EAI-003-CP | Transmission Reliability - Meeting Planning Criteria | Fordyce: Relocate capacitor bank to 115 kV bus | EAI | 2014 Summer | Proposed & In Target | Design/Scoping
11-EAI-004-1-CP | Economic | Sheridan South 500 kV FG Upgrade: Mabelvale 500 kV Substation replace 3 breakers, 13 switches, and 2 line traps | EAI | 2014 Summer | Approved | Construction
11-EAI-004-2-CP | Economic | Sheridan South 500 kV FG Upgrade: Sheridan 500 kV Substation replace 11 switches, and 6 line traps | EAI | 2014 Summer | Approved | Construction
11-EAI-004-3-CP | Economic | Sheridan South 500 kV FG Upgrade: White Bluff 500 kV Substation replace 5 switches, and 2 line traps | EAI | 2014 Summer | Approved | Construction
11-EAI-004-4-CP | Economic | Sheridan South 500 kV FG Upgrade: Eldorado 500 kV Substation replace 1 switch and 2 line traps | EAI | 2014 Summer | Approved | Construction
12-EAI-002-CP | Transmission Reliability - Meeting Planning Criteria | Woodward - Pine Bluff West - Pine Bluff McCamant: Reconductor 115 kV | EAI | 2014 Summer | Proposed & In Target | Design/Scoping
12-EAI-005-CP | Transmission Reliability - Meeting Planning Criteria | Camden McGuire - Camden North 115kV Line: Construct New Line | EAI | 2014 Summer | Proposed & In Target | Design/Scoping
12-EAI-008-01-CP | Transmission Reliability - Meeting Planning Criteria | LV Bagby to Macon Lake: Construct new 230 kV line and operate at 115 kV | EAI | 2014 Summer | Proposed & In Target | Design/Scoping |  | Project split into two phases. Formerly 12-EAI-008-CP
12-EAI-023-CP | Transmission Reliability - Meeting Planning Criteria | Woodward to Pine Bluff Watson Chapel: Rebuild line to 230 kV construction and operate at 115 kV. | EAI | 2014 Summer | Proposed & In Target | Design/Scoping |  | Project description changed to reflect 230 kV construction
12-EAI-024-CP | Transmission Reliability - Meeting Planning Criteria | Reconductor Arklahoma No. 2 to HS EHV East | EAI | 2014 Summer | Proposed & In Target | Design/Scoping
12-EAI-025-CP | Transmission Reliability - Meeting Planning Criteria | Reconductor Arklahoma No. 1 to HS EHV West | EAI | 2014 Summer | Proposed & In Target | Design/Scoping
12-EAI-001-CP | Transmission Reliability - Meeting Planning Criteria | Calico Rock-Melbourne - Upgrade 161kV Line | EAI | 2014 Winter | Proposed & In Target | Design/Scoping
11-EAI-007-CP | Transmission Reliability - Meeting Planning Criteria | Hot Springs Hamilton (Albright) - Carpenter Dam: Construct new 115 kV Liine and convert Mountain Pine South to ring bus stations. | EAI | 2015 Summer | Proposed & In Target | Design/Scoping
13-EAI-003-CP | Transmission Reliability - Meeting Planning Criteria | Monticello East to Reed: Construct new 115 kV transmission line. Construct to 230 kV but operate at 115 kV. | EAI | 2015 Summer | Proposed & In Target | Design/Scoping |  | Replaces Monticello East SVC project 12-EAI-007-CP
11-EAI-008-CP | Transmission Reliability - Meeting Planning Criteria | Pine Bluff Voltage Support Project: Phase 2 Woodward: Construct 230 kV ring bus and construct new White Bluff to Woodward 230 kV line | EAI | 2015 Summer | Proposed & In Target | Design/Scoping
11-EAI-017-CP | Transmission Reliability - Meeting Planning Criteria | White Bluff: Reconfigure 500 kV Station and construct 230 kV ring bus | EAI | 2015 Summer | Proposed & In Target | Design/Scoping
12-EAI-016-CP | Transmission Reliability - Meeting Planning Criteria | HS EHV-HS Industrial: Upgrade Terminal Equipment | EAI | 2015 Summer | Proposed & In Target | Design/Scoping
12-EAI-017-CP | Transmission Reliability - Meeting Planning Criteria | HS Industrial-HS Union Carbide: Upgrade Terminal Equipment | EAI | 2015 Summer | Proposed & In Target | Design/Scoping
12-EAI-018-CP | Transmission Reliability - Meeting Planning Criteria | HS Union Carbide-HS East: Upgrade Terminal Equipment | EAI | 2015 Summer | Proposed & In Target | Design/Scoping
11-EAI-025-CP | Transmission Reliability - Meeting Planning Criteria | Norfork-Calico Rock : Upgrade 161 kV Line | EAI | 2016 Summer | Proposed & In Target | Design/Scoping
11-EAI-027-CP | Transmission Reliability - Meeting Planning Criteria | AECC L&D 2 to Gillett: Construct new 115 kV Line | EAI | 2016 Summer | Proposed & In Target | Design/Scoping
12-EAI-003-CP | Transmission Reliability - Meeting Planning Criteria | Woodward-115 kV Bus Reconfiguration | EAI | 2016 Summer | Proposed & In Target | Design/Scoping
12-EAI-019-CP | Transmission Reliability - Meeting Planning Criteria | Mabelvale: Replace 500-115 Autos | EAI | 2016 Summer | Proposed & In Target | Design/Scoping
13-EAI-001-CP | Transmission Reliability - Meeting Planning Criteria | Pine Bluff McCamant- Pine Bluff East: Reconductor line | EAI | 2016 Summer | Proposed & In Target | Design/Scoping
12-EAI-035-CP | Transmission Reliability - Meeting Planning Criteria | Ward: Install 21.6 MVAR capacitor bank | EAI | 2016 Summer | Proposed & In Target | Design/Scoping
11-EAI-015-CP | Transmission Reliability - Meeting Planning Criteria | Jim Hill Area Upgrades Doniphan (AECI New Sub) - Datto 161 construct new line | EAI | 2017 Summer | Proposed & In Target | Design/Scoping
12-EAI-027-CP | Transmission Reliability - Meeting Planning Criteria | Malvern South: Add 10.2 MVAR Capacitor Bank | EAI | 2017 Summer | Proposed & In Target | Design/Scoping
12-EAI-008-02-CP | Transmission Reliability - Meeting Planning Criteria | Macon Lake to Reed: Construct new 230 kV line and operate at 115 kV | EAI | 2017 Summer | Proposed & In Target | Design/Scoping |  | Project split into two phases. Formerly 12-EAI-008-CP
12-EAI-028_HZ | Transmission Reliability - Meeting Planning Criteria | Change Danville 161-115 Auto tap to 115.5 kV | EAI | 2017 Summer | Proposed & In Target | Design/Scoping
13-EAI-002-CP | Transmission Reliability - Meeting Planning Criteria | Pine Bluff Watson Chapel - Pine Bluff South: Rebuild line to 230 kV construction and operate at 115 kV | EAI | 2017 Summer | Proposed & In Target | Design/Scoping |  | Project description changed to reflect 230 kV construction
12-EAI-021-CP | Enhanced Transmission Reliability | Mayflower - Reconfigure 500 kV bus (eliminate breaker failure impact on autos) | EAI | 2017 Winter | Proposed & In Target | Design/Scoping
11-EAI-016-CP | Transmission Reliability - Meeting Planning Criteria | ISES- Reconfiguration of the 161kV Bus | EAI | 2018 Summer | Proposed & In Target | Design/Scoping
11-EAI-024-CP | Transmission Reliability - Meeting Planning Criteria | Holland Bottoms to Jacksonville North: Reconductor 115 kV Line | EAI | 2018 Summer | Proposed & In Target | Design/Scoping
12-EAI-006-CP | Transmission Reliability - Meeting Planning Criteria | Russellville East-Russellville North: Reconductor 161kV line | EAI | 2018 Summer | Proposed & In Target | Design/Scoping
12-EAI-009-CP | Transmission Reliability - Meeting Planning Criteria | LR West-LR Palm: Reconductor 115kV line | EAI | 2018 Summer | Proposed & In Target | Design/Scoping
12-EAI-010-CP | Transmission Reliability - Meeting Planning Criteria | NLR Westgate-LR Gaines: Reconductor 115kV line | EAI | 2018 Summer | Proposed & In Target | Design/Scoping
12-EAI-014-CP | Transmission Reliability - Meeting Planning Criteria | Mabelvale-Bryant: Reconductor 115kV line | EAI | 2018 Summer | Proposed & In Target | Design/Scoping
12-EAI-029-CP | Transmission Reliability - Meeting Planning Criteria | Upgrade Cheetah to Hot Springs Village 115 kV line | EAI | 2018 Summer | Proposed & In Target | Design/Scoping
12-EAI-031-CP | Transmission Reliability - Meeting Planning Criteria | LR Kanis to LR Markham: Reconductor line | EAI | 2018 Summer | Proposed & In Target | Design/Scoping
12-EAI-032-01-CP | Transmission Reliability - Meeting Planning Criteria | Construct Gum Springs Switching Station | EAI | 2018 Summer | Proposed & In Target | Design/Scoping
12-EAI-032-02-CP | Transmission Reliability - Meeting Planning Criteria | Gum Springs to Amity construct new line. Add breakers at Amity | EAI | 2018 Summer | Proposed & In Target | Design/Scoping
10-EGL-007-1-CP | Transmission Reliability - Meeting Planning Criteria | Acadiana Area Improvement Project Phase 2 Projects Construct new Labbe to Sellers Road 230 kV Line | EGSL | 2012 Summer | Approved | Complete | 2012-06-28
10-EGL-007-2-CP | Transmission Reliability - Meeting Planning Criteria | Acadiana Area Improvement Project Phase 2 Projects Add new 500 kV position for Cleco autotransformer at Wells | EGSL | 2012 Summer | Approved | Complete | 2011-05-06
10-EGL-008-CP | Transmission Reliability - Meeting Planning Criteria | Construct new Nelson to Moss Bluff 230 kV line Disconnect existing Nelson to Moss Bluff 230 kV line Will be used in the future to create a Nelson to new Lake Charles 230 kV line | EGSL | 2012 Summer | Approved | Complete | 2012-05-12
10-EGL-009-CP | Transmission Reliability - Meeting Planning Criteria | Tejac to Marydale: Upgrade 69 kV transmission line | EGSL | 2012 Summer | Approved | Complete | 2012-02-15
11-EGL-005-CP | Transmission Reliability - Meeting Planning Criteria | Jackson to Tejac: Upgrade 69 kV transmission line | EGSL | 2012 Summer | Approved | Complete | 2012-06-15
11-EGL-013-CP | Transmission Reliability - Meeting Planning Criteria | Fireco to Copol 69 kV line: Upgrade switches and line trap | EGSL | 2012 Summer | Approved | Complete | 2012-05-21
11-EGL-014-CP | Transmission Reliability - Meeting Planning Criteria | Addis 69 kV substation: Upgrade 69 kV switches and line trap | EGSL | 2012 Summer | Approved | Complete | 2012-05-21
12-EGL-014-CP | Transmission Reliability - Meeting Planning Criteria | Lake Charles Bulk Substation: Replace four 69 kV, 600 A switches on transformers and bus section breaker with 1200 A switches | EGSL | 2012 Fall | Approved | Design |  | Project delayed to Fall due to construction feasiblity
11-EGL-013-1-CP | Transmission Reliability - Meeting Planning Criteria | Fireco to Copol 69 kV line: Upgrade line conductor | EGSL | 2012 Winter | Approved | Design/Scoping
10-EGL-011-CP | Transmission Reliability - Meeting Planning Criteria | Mossville - Cut-in line 616 (Nelson to Carlyss 138 kV) into Mossville 138 kV Substation | EGSL | 2013 Summer | Proposed & In Target | Design/Scoping
10-EGL-013-CP | Transmission Reliability - Meeting Planning Criteria | Krotz Springs to Line 642 Tap 138 kV line: Upgrade bus at Colonial Springs Tap | EGSL | 2013 Summer | Approved | Complete | 2011-03-14
11-EGL-004-CP | Transmission Reliability - Meeting Planning Criteria | Bloomfield to Bosco 138 kV line (formerly Vatican project) Construct new Bloomfield 138 kV SS north of Vatican Construct new Bosco 138 kV SS on Scott to Scanlan 138 kV line Construct new Bloomfield to Bosco 138 kV line Install 5 ohm reactor at Bosco substation | EGSL | 2013 Summer | Approved | Design/Scoping
11-EGL-008-CP | Transmission Reliability - Meeting Planning Criteria | Francis 69 kV substation - Add 14.4 MVAR, 69 kV capacitor bank (Previously considered Marydale as altenative location) | EGSL | 2013 Summer | Approved | Design/Scoping
11-EGL-015-1-CP | Transmission Service | Acadia Generation - Reconfigure Richard 138 kV substation (Upgrade ckts 3 and 4 and Richard relaying work) | EGSL | 2013 Summer | Approved | Complete | 2012-05-15
11-EGL-015-3-CP | Transmission Service | Acadia Generation - Upgrade Moril to Hopkins 138 kV line | EGSL | 2013 Summer | Approved | Design/Scoping
11-EGL-015-4-CP | Transmission Service | Acadia Generation - Upgrade 69 kV breaker at Scott 18220 | EGSL | 2013 Summer | Approved | Design/Scoping
12-EGL-003-CP | Transmission Reliability - Meeting Planning Criteria | Champagne to Plaisance 138 kV line - Modify/Replace CTs at Champagne | EGSL | 2013 Summer | Proposed & In Target | Design/Scoping
11-EGL-012-CP | Transmission Reliability - Meeting Planning Criteria | Carlyss to Nelson 230 kV: Upgrade station equipment at Carlyss | EGSL | 2013 Winter | Approved | Complete | 2011-06-09
11-EGL-016-01-CP | Transmission Reliability - Meeting Planning Criteria | Mossville to Canal - Phase 1: Upgrade 69 kV Line | EGSL | 2013 Winter | Proposed & In Target | Design/Scoping |  | Project split into two phases. Formerly 11-EGL-016-CP
12-EGL-015-CP | Economic | Willow Glen to Conway - Construct new 230 kV line | EGSL | 2013 Winter | Approved | Design
11-EGL-016-02-CP | Transmission Reliability - Meeting Planning Criteria | Mossville to Canal - Phase 2: Upgrade 69 kV Line | EGSL | 2014 Winter | Proposed & In Target | Design/Scoping |  | Project split into two phases. Formerly 11-EGL-016-CP
12-EGL-008-CP | Transmission Reliability - Meeting Planning Criteria | Copol to Bourbeaux: Upgrade 69 kV line | EGSL | 2014 Winter | Approved | Design/Scoping
12-EGL-006-CP | Transmission Reliability - Meeting Planning Criteria | Bronco - New 230 kV distribution substation (Formerly called Zachery) | EGSL | 2017 Summer | Proposed & In Target | Design/Scoping
12-EGL-004-CP | Transmission Reliability - Meeting Planning Criteria | McManus to Brady Heights - Upgrade 69 kV line | EGSL | 2017 Winter | Proposed & In Target | Design/Scoping
11-EGL-002-CP | Transmission Reliability - Meeting Planning Criteria | Harelson to Gloria - upgrade 69 kV line | EGSL | 2018 Summer | Proposed & In Target | Design/Scoping
11-EGL-017-CP | Transmission Reliability - Meeting Planning Criteria | Five Points to Line Tap 281 to Line 247 Tap- Upgrade 69 kV line | EGSL | 2018 Winter | Proposed & In Target | Design/Scoping
10-EGL-010-CP | Transmission Reliability - Meeting Planning Criteria | Loblolly-Hammond Build 230 kV Line | EGSL/ELL | 2012 Summer | Approved | Complete | 2011-12-16
11-EGL-010-CP | Transmission Reliability - Meeting Planning Criteria | Sorrento Upgrade 138/115 kV Auto and upgrade Gonzales - Sorrento 138 kV Line | EGSL/ELL | 2014 Summer | Proposed & In Target | Design/Scoping
10-ELL-010-1-CP | Transmission Service | Ouachita Transmission Service Split Sterlington 115 kV bus and replace 500-115 auto #2 with 750 MVA | ELL | 2012 Summer | Approved | Complete | 2012-03-12
10-ELL-010-4-CP | Transmission Service | Ouachita Transmission Service Upgrade Sterlington to Log Cabin 115 kV line | ELL | 2012 Summer | Approved | Complete | 2011-12-20
10-ELL-010-5-CP | Transmission Reliability - Meeting Planning Criteria | Ouachita Transmission Service Loop Sterlington to North Crossett into North Bastrop | ELL | 2012 Summer | Approved | Complete | 2011-06-15
12-ELL-001-CP | Transmission Reliability - Meeting Planning Criteria | Gypsy to Luling: Upgrade line bay bus and jumpers at Luling | ELL | 2012 Summer | Approved | Complete | 2011-12-22
10-ELL-007-CP | Transmission Reliability - Meeting Planning Criteria | Southeast LA Coastal Improvement Plan: Phase 2 Build Peters Road-Oakville 230kV Line and Substation | ELL | 2012 Fall | Approved | Design/Construction
10-ELL-010-2-CP | Transmission Service | Ouachita Transmission Service Upgrade Walnut Grove to Swartz 115 kV line | ELL | 2013 Spring | Approved | Complete | 2012-04-17
10-ELL-008-CP | Transmission Reliability - Meeting Planning Criteria | Southeast LA Coastal Improvement Plan: Phase 3 Construct Oakville to Alliance 230kV Line Add 230 - 115 kV Autotransformer at Alliance Substation | ELL | 2013 Summer | Approved | Design/Construction |  | ISD reflects constructrion feasibility. Moved from 2012 Winter
11-ELL-003-1-CP | Transmission Reliability - Meeting Planning Criteria | NE Louisiana Improvement Project - Phase 1 Swartz to Oakridge - Construct new 115 kV Line (1272 ACSS) Operate Sterlington to Oakridge normally open | ELL | 2013 Summer | Approved | Design/Scoping
13-ELL-001-CP | Transmission Reliability - Meeting Planning Criteria | Golden Meadow to Barataria: Upgrade switch | ELL | 2013 Summer | Proposed & In Target | Design/Scoping
13-ELL-002-CP | Transmission Reliability - Meeting Planning Criteria | Napoleonville 115 kV Substation: Add 20.4 MVAR Capacitor Bank | ELL | 2013 Summer | Proposed & In Target | Design/Scoping
11-ELL-001-CP | Enhanced Transmission Reliability | Golden Meadow to Leeville 115 kV - Rebuild/relocate 115 kV transmission line | ELL | 2013 Winter | Approved | Design/Scoping
11-ELL-002-CP | Transmission Reliability - Meeting Planning Criteria | Mt. Olive: Add Shunt Reactor | ELL | 2013 Winter | Proposed & In Target | Design/Scoping
11-ELL-003-2-CP | Transmission Reliability - Meeting Planning Criteria | NE Louisiana Improvement Project - Phase 2 Oakridge to new Dunn Substation - Construct new 115 kV Line (1272 ACSS) Add 115 kV breakers at Dunn | ELL | 2014 Summer | Approved | Design/Scoping
13-ELL-003-CP | Transmission Reliability - Meeting Planning Criteria | Hodge area voltage support: Source Jonesboro substation from Danville | ELL | 2014 Summer | Proposed & In Target | Design/Scoping
11-ELL-009-1-CP | Generation Interconnection | NM6: Modify Ninemile switchyard for interconnection | ELL | 2014 Winter | Approved | Design/Scoping
11-ELL-009-2-CP | Generation Interconnection | NM6: Upgrade Michoud breaker N9803 | ELL | 2014 Winter | Approved | Design/Scoping
11-ELL-010-1-CP | Transmission Service | NM6: Upgrade Ninemile to Southport 230 kV transmission line No.1 | ELL | 2014 Winter | Approved | Design/Scoping
11-ELL-010-2-CP | Transmission Service | NM6: Upgrade Ninemile to Southport 230 kV transmission line No.2 | ELL | 2014 Winter | Approved | Design/Scoping
10-ELL-009-CP | Transmission Reliability - Meeting Planning Criteria | Iron Man to Tezcuco 230 kV line - Construct new line | ELL | 2015 Summer | Approved | Design/Construction
11-ELL-005-CP | Transmission Reliability - Meeting Planning Criteria | Mt. Olive to Arcadia Project Phase 1 Add 115 kV breakers at Arcadia for future Mt. Olive to Arcadia line | ELL | 2015 Summer | Proposed & In Target | Design/Scoping
11-ELL-012-CP | Transmission Reliability - Meeting Planning Criteria | Valentine to Clovelly 115 kV upgrade | ELL | 2015 Summer | Proposed & In Target | Design/Scoping
13-ELL-004-CP | Transmission Reliability - Meeting Planning Criteria | Minden Improvement Project Ph 1-Place cap bank at Minden REA | ELL | 2015 Summer | Proposed & In Target | Design/Scoping
11-ELL-004-CP | Transmission Reliability - Meeting Planning Criteria | Northeast LA Improvement Project Phase 3 Upgrade Sterlington to Oakridge to Dunn 115 kV Line | ELL | 2015 Summer | Proposed & In Target | Design/Scoping
10-EMI-012-1-CP | Transmission Reliability - Meeting Planning Criteria | Ridgeland-Madison Reliability Improvement Rebuild Lakeover - Ridgeland Line | EMI | 2012 Summer | Approved | Complete | 2012-05-30
10-EMI-012-2-CP | Transmission Reliability - Meeting Planning Criteria | Ridgeland-Madison Reliability Improvement Build Lakeover - Sunnybrook - Northpark 115 kV Line | EMI | 2012 Summer | Approved | Complete | 2012-05-30
10-EMI-013-CP | Transmission Service | Ouachita Transmission Service Move Sterlington 600 MVA auto to Baxter Wilson 500 (Second 500-115 kV auto) | EMI | 2012 Summer | Approved | Complete | 2012-06-26
10-EMI-014-1-CP | Transmission Reliability - Meeting Planning Criteria | Grenada/Winona/Greenwood Area Improvement (Tillatoba auto alternative): Phase 2 Projects Tillatoba to South Grenada 230 kV Line: Construct New 520 MVA Line | EMI | 2012 Summer | Approved | Complete | 2012-06-11
10-EMI-014-2-CP | Transmission Reliability - Meeting Planning Criteria | Grenada/Winona/Greenwood Area Improvement (Tillatoba auto alternative): Phase 2 Projects South Grenada 115 kV Substation: Install 230 kV Bus and a 400 MVA 230-115 kV Autotransformer | EMI | 2012 Summer | Approved | Complete | 2012-06-11
11-EMI-004-CP | Transmission Reliability - Meeting Planning Criteria | Ray Braswell to West Jackson 115 kV line: Reconductor line | EMI | 2012 Summer | Approved | Design |  | May be delayed to the winter due to construction feasibility
12-EMI-003-CP | Transmission Reliability - Meeting Planning Criteria | Northeast Jackson to Klean Steel - Upgrade CT and Jumpers/Risers at NE Jackson | EMI | 2012 Summer | Approved | Complete | 2011-12-07
10-EMI-017-CP | Transmission Reliability - Meeting Planning Criteria | Ray Braswell - Wyndale 115kV Line: Construct New 260 MVA Construct new 115 kV Switching Station between Byram and Terry Wyndale SS to be designed for future 230-115 kV auto and distribution facilities | EMI | 2013 Summer | Approved | Construction
10-EMI-018-CP | Transmission Reliability - Meeting Planning Criteria | Getwell to Church Road 230 kV construct new 230 kV Transmission Line | EMI | 2013 Summer | Approved | Design
13-EMI-001-CP | Transmission Reliability - Meeting Planning Criteria | Upgrade CTs at Vicksburg for Vicksburg-B.Wilson ckt 1 (ckt without Spencer Potash on it) | EMI | 2013 Summer | Proposed & In Target | Design
13-EMI-006-CP | Enhanced Transmission Reliability | Bolton 115 kV Substation: Add 115 kV breakers | EMI | 2013 Summer | Proposed & In Target | Design |  | New Project
13-EMI-004-CP | Transmission Service | SMEPA Plum Point Transmission Service: Horn Lake to Greenbrook 115 kV line: Upgrade station equipment at Horn Lake | EMI | 2013 Summer | Approved | Design |  | New Project
11-EMI-002-CP | Transmission Reliability - Meeting Planning Criteria | Baxter Wilson to S.E. Vicksburg - Upgrade 115 kV line | EMI | 2015 Summer | Proposed & In Target | Design/Scoping
11-EMI-007-CP | Transmission Reliability - Meeting Planning Criteria | Breakers at Hollandale and Belzoni (close normally-open point) | EMI | 2015 Summer | Proposed & In Target | Design/Scoping
12-EMI-002-1-CP | Transmission Reliability - Meeting Planning Criteria | Getwell Area Improvements Construct new Senatobia Industrial substation. Cut in Senatobia to Sardis 115 kV line into new substation and add new 230-115 kV autotransformer | EMI | 2016 Summer | Proposed & In Target | Design/Scoping
12-EMI-002-2-CP | Transmission Reliability - Meeting Planning Criteria | Getwell Area Improvements Construct new 230 kV line from Getwell to new Senatobia Industrial 230-115 kV substation. | EMI | 2016 Summer | Proposed & In Target | Design/Scoping
12-EMI-001-CP | Transmission Reliability - Meeting Planning Criteria | Franklin - McComb build new 115 kV line (constructed to 230 kV) Also upgrade all substation elements along Tylertown to McComb 115 kV line to provide a minimum 1000A rating. | EMI | 2017 Summer | Proposed & In Target | Design/Scoping
13-EMI-002-CP | Transmission Reliability - Meeting Planning Criteria | Durant: Add Capacitor Bank | EMI | 2017 Summer | Proposed & In Target | Design
11-EMI-006-CP | Transmission Reliability - Meeting Planning Criteria | Reconductor E.Vicksburg-Edwards 115kV | EMI | 2018 Summer | Proposed & In Target | Design
11-ETI-004-CP | Transmission Reliability - Meeting Planning Criteria | Elizabeth to Gallier - Uprate 69 kV line 2.5 miles | ETI | 2012 Summer | Approved | Complete | 2011-09-14
11-ETI-006-CP | Transmission Reliability - Meeting Planning Criteria | Somerville 69 kV Substation: Add capacitor bank | ETI | 2012 Summer | Approved | Complete | 2012-05-15
12-ETI-015-CP | Enhanced Transmission Reliability | College Station SS: Create emergency tie point with ERCOT (asynchronous) | ETI | 2012 Fall | Approved | Construction |  | Projected ISD moved to Fall 2012. Entergy has completed all possible work and is waiting on the City of College Station to complete their work.
11-ETI-003-CP | Transmission Reliability - Meeting Planning Criteria | Deweyville (JNEC) - Add 69 kV capacitor bank | ETI | 2013 Spring | Proposed & In Target | Design/Scoping
10-ETI-017-CP | Transmission Reliability - Meeting Planning Criteria | Jasper to Rayburn 138 kV line: Upgrade | ETI | 2013 Summer | Proposed & In Target | Design/Scoping
11-ETI-008-01-CP | Transmission Reliability - Meeting Planning Criteria | Plantation to Conroe 138 kV line: Upgrade station equipment at Plantation | ETI | 2013 Summer | Proposed & In Target | Design/Scoping
11-ETI-008-CP | Transmission Reliability - Meeting Planning Criteria | Cedar Hill to Plantation 138 kV line: Upgrade line conductor and station equipment at Plantation | ETI | 2013 Summer | Proposed & In Target | Design/Scoping
11-ETI-036-CP | Transmission Reliability - Meeting Planning Criteria | Plantation to Conroe 138 kV line: Reconductor Line | ETI | 2013 Summer | Proposed & In Target | Design/Scoping
11-ETI-041-CP | Transmission Reliability - Meeting Planning Criteria | Eastgate to Dayton Bulk: Upgrade terminal equipment at Eastgate (formerly reconductor) | ETI | 2013 Summer | Proposed & In Target | Design/Scoping
11-ETI-043-CP | Transmission Reliability - Meeting Planning Criteria | Expand Cap Bank at Calvert 69kV | ETI | 2013 Summer | Proposed & In Target | Design/Scoping
12-ETI-003-CP | Transmission Reliability - Meeting Planning Criteria | Bentwater Substation: Add 138 kV Capacitor Bank | ETI | 2013 Summer | Proposed & In Target | Design/Scoping
12-ETI-004-CP | Transmission Reliability - Meeting Planning Criteria | Ponderosa Switching Station: tie lines Longmire to Fish Creek and Conroe to Woodhaven into new switching station | ETI | 2013 Summer | Proposed & In Target | Design/Scoping
11-ETI-009-CP | Transmission Reliability - Meeting Planning Criteria | Toledo Bend to Leach 138 kV line: Upgrade station equipment at Toledo Bend | ETI | 2013 Winter | Approved | Complete | 2011-11-28
11-ETI-010-CP | Transmission Reliability - Meeting Planning Criteria | Leach to Newton Bulk 138 kV line: Upgrade terminal equipment at Newton Bulk | ETI | 2013 Winter | Proposed & In Target | Design/Scoping
11-ETI-039-CP | Transmission Reliability - Meeting Planning Criteria | Upgrade Jacinto - Splendora 138 kV Line | ETI | 2015 Summer | Proposed & In Target | Design/Scoping
12-ETI-007-CP | Transmission Reliability - Meeting Planning Criteria | Alden 138 kV Substation: Add Capacitor Bank | ETI | 2015 Summer | Proposed & In Target | Design/Scoping
13-ETI-001-CP | Transmission Reliability - Meeting Planning Criteria | Porter Var Support: Add 36 MVAR capacitor bank at Porter | ETI | 2015 Summer | Proposed & In Target | Design/Scoping
11-ETI-042-CP | Transmission Reliability - Meeting Planning Criteria | Expand Cap Bank at New Caney 138kV | ETI | 2015 Summer | Proposed & In Target | Design/Scoping
11-ETI-018-CP | Transmission Reliability - Meeting Planning Criteria | Construct new China to Amelia 230kV line | ETI | 2016 Summer | Proposed & In Target | Design/Scoping
11-ETI-020-CP | Transmission Reliability - Meeting Planning Criteria | Hickory Ridge-Eastgate 138kV: Upgrade terminal equipment at Eastgate | ETI | 2016 Summer | Proposed & In Target | Design/Scoping
11-ETI-026-CP | Transmission Reliability - Meeting Planning Criteria | Upgrade Splendora to Apollo 138 kV Line | ETI | 2016 Summer | Proposed & In Target | Design/Scoping
13-ETI-009-01-CP | Transmission Reliability - Meeting Planning Criteria | Ponderosa to Grimes: Construct new 230 kV Line Add 345-230 kV Auto at Grimes Add 230-138 kV Auto at Ponderosa | ETI | 2016 Summer | Proposed & In Target | Design/Scoping |  | New Project. Replaces 12-ETI-002-CP, 11-ETI-014-HZ, 11-ETI-013-HZ, and 12-ETI-016-HZ
13-ETI-009-02-CP | Transmission Reliability - Meeting Planning Criteria | Conroe to Ponderosa 138 kV line: Upgrade Line | ETI | 2016 Summer | Proposed & In Target | Design/Scoping |  | New Project. Replaces 12-ETI-002-CP, 11-ETI-014-HZ, 11-ETI-013-HZ, and 12-ETI-016-HZ
11-ETI-019-CP | Transmission Reliability - Meeting Planning Criteria | Cut Line 871 Jacinto to Splendora 138 kV line into the Cleveland 138 kV substation. | ETI | 2017 Summer | Proposed & In Target | Design/Scoping
11-ETI-023-CP | Transmission Reliability - Meeting Planning Criteria | Orange County 230kV Project: Construct new Chisholm Road 230 kV substation, Construct new line from Hartburg to Chisholm Road, add 2nd Hartburg 500-230 kV auto | ETI | 2017 Summer | Proposed & In Target | Design/Scoping
11-ETI-033-CP | Transmission Reliability - Meeting Planning Criteria | Toledo Bend to Leach 138 kV - Upgrade line | ETI | 2017 Summer | Proposed & In Target | Design/Scoping
11-ETI-002-CP | Transmission Reliability - Meeting Planning Criteria | Reconductor Sabine to Port Neches Bulk (Line 515) | ETI | 2017 Summer | Proposed & In Target | Design/Scoping
12-ETI-009-CP | Transmission Reliability - Meeting Planning Criteria | Sabine: Upgrade terminal equipment (Sabine to Big 3 line) | ETI | 2017 Summer | Proposed & In Target | Design/Scoping
11-ETI-016-CP | Transmission Reliability - Meeting Planning Criteria | Add 2nd Cypress Auto 500/138kV | ETI | 2018 Summer | Proposed & In Target | Design/Scoping
11-ETI-022-CP | Transmission Reliability - Meeting Planning Criteria | Western Region Reliability Improvement Plan : Add Alden SVC | ETI | 2018 Summer | Proposed & In Target | Design/Scoping
11-ETI-034-CP | Transmission Reliability - Meeting Planning Criteria | Leach to Newton Bulk 138 kV - Reconductor line | ETI | 2018 Summer | Proposed & In Target | Design/Scoping
11-ETI-037-CP | Transmission Reliability - Meeting Planning Criteria | Construct new China to Stowell 138 kV line | ETI | 2018 Summer | Proposed & In Target | Design/Scoping
11-ETI-038-CP | Transmission Reliability - Meeting Planning Criteria | Reconductor Sabine to Port Neches Bulk (via Linde Line 516) | ETI | 2018 Summer | Proposed & In Target | Design/Scoping
12-ETI-014-CP | Transmission Reliability - Meeting Planning Criteria | Amelia to Helbig: Upgrade line | ETI | 2018 Summer | Proposed & In Target | Design/Scoping |  | Accelerated from Horizon Plan
12-ETI-002-CP | Transmission Reliability - Meeting Planning Criteria | Grimes Substation - Add 3rd 345-138 kV Auto | ETI | 2018 Summer | Proposed & In Target | Design/Scoping |  | Replaced by 13-ETI-009-01-CP and 13-ETI-009-02

## Horizon Projects Header
Addendum Horizon Projects [Beyond Construction Plan]
Horizon Projects are projects identified in the annual 10 year reliability assesment but are not included in the current five year construction plan window. Final project scopes and timing may vary in future assessments.

## Horizon Projects
Horizon Projects are projects identified in the annual 10 year reliability assesment but are not included in the current five year construction plan window. Final project scopes and timing may vary in future assessments.
Horizon Project ID | Project Driver | Project Name | LE | Proposed Planning ISD | Project Status | Other Comments
12-EAI-011-HZ | Transmission Reliability - Meeting Planning Criteria | Paragould-Paragould South: Reconductor 161kV line | EAI | 2020 Summer | Conceptual
12-EAI-012-HZ | Transmission Reliability - Meeting Planning Criteria | LR Boyle Park-LR West: Upgrade Terminal Equipment | EAI | 2020 Summer | Conceptual
12-EAI-013-HZ | Transmission Reliability - Meeting Planning Criteria | LR Mann Road-LR Chicot: Upgrade Terminal Equipment | EAI | 2020 Summer | Conceptual
12-EAI-033-HZ | Transmission Reliability - Meeting Planning Criteria | Hergett: Add 36 MVAR Capacitor Bank | EAI | 2020 Summer | Conceptual
12-EAI-034-HZ | Transmission Reliability - Meeting Planning Criteria | Jonesboro to Jonesboro SPA reconductor line | EAI | 2020 Summer | Conceptual
13-EAI-006-HZ | Transmission Reliability - Meeting Planning Criteria | Cabot: Install 21.6 MVAR capacitor bank | EAI | 2020 Summer | Conceptual | New Project
13-EAI-005-HZ | Transmission Reliability - Meeting Planning Criteria | Bryant: Install 21.6 MVAR capacitor bank | EAI | 2021 Summer | Conceptual | New Project
12-EGL-010-HZ | Transmission Reliability - Meeting Planning Criteria | New Iberia: Add 138-69 kV transformer | EGSL | 2018 Summer | Conceptual
12-EGL-001-HZ | Transmission Reliability - Meeting Planning Criteria | Juban: Construct a new 230 kV Distribution substation. (Formerly called Lockhart) | EGSL | 2020 Summer | Conceptual | Dependent of future block load addtion
12-EGL-009-HZ | Transmission Reliability - Meeting Planning Criteria | Harleson to 372A Tap: Upgrade line | EGSL | 2020 Summer | Conceptual
13-EGL-002-HZ | Transmission Reliability - Meeting Planning Criteria | Lake Arthur 69 kV: Move normally open point | EGSL | 2020 Summer | Conceptual | New Project
11-EGL-007-HZ | Transmission Reliability - Meeting Planning Criteria | Moril to Delcambre 138 kV line: Upgrade station equipment | EGSL | 2021 Summer | Conceptual
11-EGL-018-HZ | Transmission Reliability - Meeting Planning Criteria | Francis to Marydale: Upgrade 69 kV line | EGSL | 2023 Summer | Conceptual
13-EGL-001-HZ | Transmission Reliability - Meeting Planning Criteria | Serpent 69 kV Substation: Upgrade capacitor bank to 11.2 MVAR | EGSL | 2023 Summer | Conceptual
11-ELL-011-HZ | Transmission Reliability - Meeting Planning Criteria | Mt. Olive to Arcadia Project Phase 2 Construct new 230 kV line (operate at 115 kV) from Mt. Olive to Arcadia | ELL | 2020 Summer | Conceptual
13-ELL-005-HZ | Transmission Reliability - Meeting Planning Criteria | Vienna to Ruston Frazier Road 115 kV Line 173: Upgrade metering CTs at Ruston | ELL | 2023 Summer | Conceptual
13-EMI-005-HZ | Transmission Reliability - Meeting Planning Criteria | Charity Church 230 kV: Add Capacitor Bank | EMI | 2020 Summer | Conceptual
12-ETI-006-HZ | Transmission Reliability - Meeting Planning Criteria | Kolbs 230 kV - Add capacitor bank | ETI | 2018 Summer | Conceptual
12-ETI-017-HZ | Transmission Reliability - Meeting Planning Criteria | Gulfway 230 kV substation: Upgrade equipment on VFW Park 230 kV line bay | ETI | 2018 Summer | Conceptual
13-ETI-003-HZ | Transmission Reliability - Meeting Planning Criteria | Port Acres Bulke 230 kV: Add Capacitor Banks | ETI | 2018 Summer | Conceptual | May require different locations for Var Support due to switching
12-ETI-010-HZ | Transmission Reliability - Meeting Planning Criteria | Buna: Add capacitor bank | ETI | 2018 Winter | Conceptual
11-ETI-014-HZ | Transmission Reliability - Meeting Planning Criteria | Upgrade Grimes to Mt. Zion 138 kV line | ETI | 2019 Summer | Conceptual | Replaced by 13-ETI-009-01-CP and 13-ETI-009-02
12-ETI-011-HZ | Transmission Reliability - Meeting Planning Criteria | Buna to Evadale: Upgrade Line | ETI | 2019 Winter | Conceptual
11-ETI-017-HZ | Transmission Reliability - Meeting Planning Criteria | Add Cap Bank at Huntsville 138kV | ETI | 2020 Summer | Conceptual
13-ETI-004-HZ | Transmission Reliability - Meeting Planning Criteria | Porter Substation: Upgrade line bay bus | ETI | 2020 Summer | Conceptual
11-ETI-013-HZ | Transmission Reliability - Meeting Planning Criteria | Upgrade Grimes to Bentwater 138 kV line | ETI | 2021 Summer | Conceptual | Replaced by 13-ETI-009-01-CP and 13-ETI-009-02
13-ETI-005-HZ | Transmission Reliability - Meeting Planning Criteria | Rayburn to Fork Creek: Upgrade to 100 deg C | ETI | 2021 Summer | Conceptual
13-ETI-006-HZ | Transmission Reliability - Meeting Planning Criteria | Staley: Add 25.1 MVAR Cap Bank | ETI | 2021 Summer | Conceptual
13-ETI-007-HZ | Transmission Reliability - Meeting Planning Criteria | Western Region Reliability Improvement Plan Phase 3 Final Construct new Cypress to Jacinto 230 kV Line with series compensation | ETI | 2021 Summer | Conceptual | Accelerated one year
11-ETI-040-HZ | Transmission Reliability - Meeting Planning Criteria | Helbig to McLewis - Reconductor with ACCC | ETI | 2022 Summer | Conceptual | Moved from Construction Plan
12-ETI-001-HZ | Transmission Reliability - Meeting Planning Criteria | Winshire 69 kV: Add capacitor bank | ETI | 2023 Summer | Conceptual
12-ETI-005-HZ | Transmission Reliability - Meeting Planning Criteria | Upgrade New Caney to Hickory Ridge 138 kV | ETI | 2023 Summer | Conceptual
12-ETI-008-HZ | Transmission Reliability - Meeting Planning Criteria | Upgrade Apollo to Porter 138 kV | ETI | 2023 Summer | Conceptual
12-ETI-013-HZ | Transmission Reliability - Meeting Planning Criteria | Stonegate: Add capacitor bank | ETI | 2023 Summer | Conceptual
12-ETI-016-HZ | Transmission Reliability - Meeting Planning Criteria | Upgrade Mt. Zion to Wyntex Tap (4L558T485 tap) 138 kV line | ETI | 2023 Summer | Conceptual | Replaced by 13-ETI-009-01-CP and 13-ETI-009-02
13-ETI-008-HZ | Transmission Reliability - Meeting Planning Criteria | Fork Creek to Turkey Creek: Upgrade to 100 deg C | ETI | 2023 Summer | Conceptual
12-ETI-012-HZ | Transmission Reliability - Meeting Planning Criteria | Rayburn to Mill Creek: Upgrade Line | ETI | 2023 Winter | Conceptual

## Target Area Header
Addendum Target Areas
Target areas are areas of interest that may require reliability improvements beyond the 10 year planning horizon.

## Target Areas
Target areas are areas of interest that may require reliability improvements beyond the 10 year planning horizon.
Project Driver | Project Name | LE | Proposed Planning ISD | Project Status | Other Comments
Transmission Reliability - Meeting Planning Criteria | Bull Shoals - Midway 161 kV Line: Upgrade | EAI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | El Dorado Upland - Texas Eastern F: New Line/ Texas Eastern F - TEF SS: Reconductor Line | EAI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Gobel Substation build at crossing point, Wabbaskeka Cap Bank, ULM Cap Bank - scope 2008 (Marvel South) | EAI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Gum Springs - Amity 115 kV Line: Construct New Line | EAI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Gum Springs Area: Construct Switching Station | EAI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Highland 161 kV: Add 24 MVAR Cap Bank | EAI | TBD | Conceptual | Formerly 11-EAI-023-HZ.
Transmission Reliability - Meeting Planning Criteria | Holland Bottoms - Searcy Price Construct new line | EAI | TBD | Conceptual | Formerly 12-EAI-030
Transmission Reliability - Meeting Planning Criteria | Holland Bottoms - Ward 115kV Line Install Breakers at AECC Ward or Construct New N.O. Line | EAI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Jonesboro Area: Construct New 500/161 kV Substation | EAI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Lake Village Bagby - Macon 115 kV Line: Upgrade | EAI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Russellville East - Russellville North 161kV Line: Upgrade | EAI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Trumann-Trumann West- Upgrade 161 kV Line | EAI | TBD | Conceptual | Formerly 11-EAI-021-CP
Transmission Reliability - Meeting Planning Criteria | Mabelvale-LR Kanis 115kV Reconductor | EAI | TBD | Conceptual | Formerly 11-EAI-019-CP
Transmission Reliability - Meeting Planning Criteria | LR South-LR Rock Creek: Upgrade Terminal Equipment | EAI | TBD | Conceptual | Formerly 12-EAI-002-HZ
Transmission Reliability - Meeting Planning Criteria | Mayflower - Morgan 115 kV Line: Upgrade | EAI | TBD | Conceptual | Formerly 11-EAI-020-HZ
Transmission Reliability - Meeting Planning Criteria | Addis 69 kV loop improvement: Upgrade both 138-69 kV autotransformers and upgrade 69 kV line (Bourbeaux to Turnerville) | EGSL | EGSL | Conceptual | Formerly 11-EGL-019-CP
Transmission Reliability - Meeting Planning Criteria | Carlyss: Upgrade existing 230-69 kV autos or add a third auto | EGSL | EGSL | Conceptual | Formerly 12-EGL-002-CP
Transmission Reliability - Meeting Planning Criteria | Catalyst 69 kV Substation: Add capacitor bank | EGSL | EGSL | Conceptual | Formerly 12-EGL-007-CP
Transmission Reliability - Meeting Planning Criteria | Champagne - Add 138 kV Capacitor Bank | EGSL | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Colonial Springs: Add capacitor bank | EGSL | TBD | Conceptual | Formerly 12-EGL-013-HZ
Transmission Reliability - Meeting Planning Criteria | Construct new 69 kV line from Mossville to Alfol | EGSL | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Convert Sunset Substation to 138 kV: Cut in Scott to East Opelousa 138 kV line. | EGSL | TBD | Conceptual | Formerly 12-EGL-005-HZ
Transmission Reliability - Meeting Planning Criteria | Greenwell Springs area reconfiguration (Coly-Polyform-Denham Springs) | EGSL | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Lawtag-Jennings: Upgrade 69kV line | EGSL | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | LC Bulk - Chlomal 69 kV Line: Reconductor line | EGSL | EGSL | Conceptual | Formerly 11-EGL-003-CP
Transmission Reliability - Meeting Planning Criteria | LC Bulk: Construct 230 kV facilities and add 230-69 kV autotransformer (LC Loop Improvement Ph 2) | EGSL | TBD | Conceptual | Formerly 12-EGL-012-HZ
Transmission Reliability - Meeting Planning Criteria | Louisiana Station to Thomas 138 kV Upgrade Line | EGSL | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Solac - Upgrade 230-69 kV Autos or add 3rd transformer | EGSL | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Arcadia to Sailes - Construct new 230 kV line (operate at 115 kV) | ELL | TBD | Conceptual | Formerly 11-ELL-013-HZ
Transmission Reliability - Meeting Planning Criteria | North Louisiana Improvement Project Phase 4 Sacksonia to Winnsboro: Construct New 115 kV Line | ELL | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | DSG Reliability Improvements: Phase 3 | ELL/ENOI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Edwards to Bolton: Reconductor line | EMI | TBD | Conceptual | Formerly 13-EMI-003-HZ
Transmission Reliability - Meeting Planning Criteria | Gerald Andrus - Add 2nd 230-115 kV autotransformer | EMI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Upgrade South Jackson - East Jackson 115kV line | EMI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Paterson: Install 230/115 kV Auto | ENOI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Construct new Jacinto to Porter 230 kV line and add 2nd auto at Porter | ETI | TBD | Conceptual
Transmission Reliability - Meeting Planning Criteria | Liberty Sub: Add 25.1 MVAR Capacitor Bank | ETI | TBD | Conceptual | Formerly 13-ETI-002-CP
Transmission Reliability - Meeting Planning Criteria | Orange to Hollywood 138 kV line - Upgrade Line | ETI/EGL | TBD | Conceptual