Fact Sheet Distributed 9/22/2009 by Entergy Texas, Inc.

Transmission Projects Facts

Sept. 22, 2009

Entergy Texas, Inc. today announced it has completed or has in construction transmission system expansions and improvements to continue to reliably serve the company’s customers in Southeast Texas.

Beaumont 69 kV Improvement Project - All lines and substations included in this project are within Beaumont city limits. This reliability project represents an investment of approximately $7.4 million.

- This project involved upgrades to transmission lines 576, 98 and 190. It also included improvements at five substations: Virginia, Lincoln, Yankee Doodle, South Beaumont and Crockett.

- All new structures are either concrete or steel; the conductors (wires) have a higher rating than what was previously in place.

- Only a brief outage was needed during construction.

- These upgraded facilities went into service recently.

- All work was completed on time and on budget.

Bolivar Peninsula - Rebuild 69 kV Line 89 from Stowell, Texas to High Island. This transmission line runs from just south of Winnie to High Island. The line mainly follows State Highway 124.

- Work on this project is having minimal impact on residents and on the coastal environment.

- Completed in late August, residential area customers in the Stowell and High island area, as well as the Bolivar peninsula will benefit from this project.

- All poles are steel and designed to hurricane hardening specifications and can withstand 140 mph winds.

After hurricane Ike, the beach was temporarily served by distribution power. Bringing the 69 kV system back into this area will create a more reliable system than the one that served this area before Hurricane Ike.

Conroe and The Woodlands – A new substation east of The Woodlands and a new transmission line along with other recently completed transmission expansions and upgrades provides continued reliability for customers in this area.

Johnstown substation – Construction is complete on this new 138 kV substation. It went into service July 24.  A newly-built transmission line connects it to Entergy’s substation in Porter, Texas.

- This represents a significant upgrade that will be used to serve commercial and residential customers in the Conroe, New Caney and Porter areas.

- The new transmission line runs from state highway 242 and crosses highway 1314.

- The 58 steel poles on line 827 are individually engineered to withstand wind forces up to 110 miles per hour and 1/2 inch of ice.

- This new substation along with other improvements in this part of the Entergy Texas service territory better serves the loads in that area and has the capacity to serve residential and commercial growth.

Egypt substation - This 138 kV substation is near the community of Egypt.

- Commissioned in 2006 this facility provides an additional point of delivery for reliable power to Entergy customers on the east side of Lake Conroe.

- The Egypt substation will also supply power to the new development Shadow Lakes on Longmire as it grows.

Bentwater substation – This 138 kV substation is now under construction. It is located off FM 1097 approximately six miles from the community of Montgomery, Texas.

- This project is currently under way.

When it is commissioned in April 2010 it will primarily benefit Entergy customers in

Bentwater and Montgomery as well as all customers on the west side of Lake Conroe.

- This facility is scheduled to be in service in April 2010 prior to summer peak demand.

- Entergy is building this station to supply service closer to the load pocket on the west side of

Lake Conroe.

Detailed information including projected in service dates of planned and approved transmission projects in Texas and within the service areas of Entergy’s other operating companies is publicly available on the public portion of Entergy’s Open Access Same-time Information System at:

TEXAS & LOUISIANA

Entergy_2009_Trans_Planning_Summit_Draft_Construction_Plan_Louisiana_and_Texas.ppt#71

###