{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":6,"n_cols":6,"rows_kept":6,"cut":false,"hidden":false,"merged":[[0,0,0,2]]}
["WASN SCHEDULED OUTAGES",null,null,"12/12/2018 TO 1/11/2019","Date Created",{"$f":"NOW()","v":"2018-12-11T13:15:55.480"}]
["Request#","Start","End","Line/Equipment(s)","Work Description","Notes and Remarks"]
["ICC-18-1909","2018-12-19T07:00:00","2018-12-20T16:00:00","TRACY-WESTLEY #1 230kV LINE (MID)","MID - Remove bird nests PER MID 18-01221-CL\r\nWES CB 2358, Scheduled Relay Testing, Calibration and Functional PER MID 18-01294-CL\r\nWES CB 2359, Scheduled Relay Testing, Calibration and Functional PER MID 18-01295-CL","TIMES INCLUDE SWITCHING. \n \nTRACY-WESTLEY #1 230kV LINE (TRY-WES1) UNAVAILABLE FOR DURATION OF OUTAGE. \n \nSCHEDULING INFO: \nOATI BANC MID IMPORT LIMITED TO ???MW. \nNOTE: THIS IS AN ELEMENT OF THE NORTHWEST POWER POOL (NWPP). \n "]
["ICC-18-1910","2018-12-19T07:00:00","2018-12-20T16:00:00","TRACY-WESTLEY #2 230kV LINE (MID)","MID - Clear 230kV Line for bird nest removal per MID 18-01222-CL\r\nWES CB 2361, Scheduled Relay Testing, Calibration and Functional PER MID 18-01296-CL\r\nWES CB 2362, Scheduled Relay Testing, Calibration and Functional PER MID 18-01297-CL","TIMES INCLUDE SWITCHING. \n \nTRACY-WESTLEY #2 230kV LINE (TRY-WES2) UNAVAILABLE FOR DURATION OF OUTAGE. \n \nSCHEDULING INFO: \nOATI BANC MID IMPORT LIMITED TO ???MW. \nNOTE: THIS IS AN ELEMENT OF THE NORTHWEST POWER POOL (NWPP). \n "]
["G-18-1951","2018-12-20T06:00:00","2018-12-20T17:00:00","ROUND MOUNTAIN-COTTONWOOD #1 230kV LINE","PG&E - Cottonwood 372 breaker maintenance, and removing 372 from bus diff. scheme. PG&E performing work on behalf of WASN.","COTTONWOOD CB 372 OPEN AND CLEARED, ROUND MOUNTAIN-COTTONWOOD #1 230kV LINE UNAVAILABLE FOR DURATION OF OUTAGE. \n \nSCHEDULING NOTE: \nTHIS IS AN ELEMENT OF THE CW-RSC CVP SCHEDULING PATH (WASN INTERNAL PATH).  \nRDM230_BG: 0/0 \nPOSSIBLE COI DE-RATE "]
["G-19-0041","2019-01-08T07:00:00","2019-01-08T16:00:00","FOLSOM 230kV MAIN BUS, FOLSOM 230kV TRANSFER BUS, FOLSOM-ROSEVILLE 230kV LINE, FOLSOM-ORANGEVALE 230kV LINE (SMUD), FOLSOM-LAKE 230kV LINE (SMUD)","WASN - \r\na.\tSAFING OF CIRCUITS RELATED TO THE 230-KV MAIN BUS LOCKOUT AND BREAKER FAILURE SCHEME.  \r\nb.\tMAIN BUS DIFF AND TRANSFORMER BUS DIFF DC CIRCUIT NEEDS TO BE SEPARATED.","FOLSOM 230kV MAIN BUS OUTAGE: \nFOLSOM-ORANGEVALE, FOLSOM-LAKE, FOLSOM-ROSEVILLE 230KV LINES OPEN ENDED AT FOLSOM AND KV4A UNAVAILABLE. \nFOLSOM UNITS 2-3 UNAVAILABLE PER WASN INFO-19-0053. \n"]